# Hawkins Cookers Limited

# Executive Summary — Project Helix

Project: Project Helix | Department: Procurement | Lead: Rohit Desai

## Project Overview

Vendor consolidation and cost optimisation across raw material supply chain. Target 12% cost reduction.

## Current Status

Status: Active
Budget: Rs 2,800,000
Spent: Rs 980,000

## Phase Summary

Phase 1: Vendor Assessment — Completed (Due: 2025-03-31)

Phase 2: Contract Renegotiation — Active (Due: 2025-07-31)

Phase 3: New Vendor Onboarding — Pending (Due: 2025-12-31)

## Key Risks

1. Timeline risk if vendor tooling is delayed beyond Q2 2025.
2. Budget overrun if additional testing cycles are required.
3. Resource availability during peak production season.

## Next Steps

• Initiate New Vendor Onboarding by 2025-12-31