## Project Budget Tracker
Project ID | Project Name | Department | Lead | Budget (Rs) | Spent (Rs) | Remaining (Rs) | Utilisation % | Status
P001 | Project Aurora | Research & Development | Neeraj Sharma | 4500000 | 2870000 | 1630000 | 63.8 | Active
P002 | Project Falcon | Quality Control | Priya Mehta | 1200000 | 1145000 | 55000 | 95.4 | Completed
P003 | Project Helix | Procurement | Rohit Desai | 2800000 | 980000 | 1820000 | 35 | Active
P004 | Project Horizon | Information Technology | Arjun Menon | 1800000 | 420000 | 1380000 | 23.3 | Active
P005 | Project Cerenity | Research & Development | Neeraj Sharma | 3200000 | 1650000 | 1550000 | 51.6 | Active

## Phase Details
Project | Phase No | Phase Name | Status | Target End
Project Aurora | 1 | Concept & Feasibility | Completed | 2024-04-30
Project Aurora | 2 | Prototype Development | Completed | 2024-09-30
Project Aurora | 3 | Pressure Testing & BIS | Active | 2025-06-30
Project Aurora | 4 | Pilot Production | Pending | 2025-12-31
Project Falcon | 1 | Audit Planning | Completed | 2024-07-31
Project Falcon | 2 | Plant-wise Inspections | Completed | 2024-10-31
Project Falcon | 3 | Report & Remediation | Completed | 2024-12-31
Project Helix | 1 | Vendor Assessment | Completed | 2025-03-31
Project Helix | 2 | Contract Renegotiation | Active | 2025-07-31
Project Helix | 3 | New Vendor Onboarding | Pending | 2025-12-31
Project Horizon | 1 | ERP Assessment | Completed | 2025-08-31
Project Horizon | 2 | AI Knowledge Assistant | Active | 2026-07-31
Project Horizon | 3 | IoT Sensor Integration | Pending | 2026-12-31
Project Cerenity | 1 | Design & Material Selection | Completed | 2025-01-31
Project Cerenity | 2 | Prototype & Tooling | Active | 2025-09-30
Project Cerenity | 3 | Production Launch | Pending | 2026-03-31